## Sheet1
| Alondra | Harry | Both
Main Task | Sub-Task | Sub-Sub Task | Sub-Sub-Sub Task | Progress (Not started = NS, In progress = IP, On hold = OH, Finished = F) | Reason for hold? | Notes | Date
IRT Project
Canopy Sensor/Structure
|  | PVC glue to fix any joints? |  | F |  | Leave unglued | 2019-03-04
|  | Count working 90 degree sensors |  | F |  | 8 | 2019-03-08
|  |  | Are the 90's 5V? How tell? | F |  | Nope, 3V medical grade (D...) | 2019-03-04
|  |  | Fix 90 degree sensors | F |  |  | 2019-03-08
|  | Extend cables |  | F |  |  | 2019-04-10
|  | Sensors ready (45+12=57) |  | IP
|  |  | Solder wire and sensor to PCB | IP
|  |  | Connector on | IP
|  |  | Address | IP
|  | "Pot" sensors |  | IP
|  |  | Pot wire in cap | IP
|  |  | Solicit ideas for how to pot - use tubing? | F |  |  | 2019-03-07
|  | Harry & Alondra to agree on finalized design |  | F |  |  | 2019-04-30
|  | Order parts |  | F |  |  | 2019-05-06
|  | Assemble structures |  | IP
|  |  | Trim 3/4" PVC extension arms (already cut & in FSP) | F
|  |  | Drill hole in canopy cap | F
|  |  | Cut 3/4" PVC arm | F
|  |  | Attach all pieces | IP
|  | Where best to place structure? In or edge of plot? |  | F |  | In row, thanks George | 2019-03-26
|  | Check on Field Setup |  | F |  |  | 2019-04-30
|  |  | If good, order 3/4x3/4x1" tee | F |  |  | 2019-04-01
|  |  | Try out with rebar | F |  |  | 2019-04-01
|  | Try out stakes |  | F |  |  | 2019-04-26
Leaf Sensor/Structure
|  | Harry & Alondra to agree on finalized design |  | F |  |  | 2019-04-30
|  | Count working 35 degree sensors |  | F |  | 46 | 2019-03-08
|  | Assemble leaf sensor structures |  | IP
|  |  | Cut 2.5' THHN wire | IP
|  |  | Tape wire to sensors | IP
|  |  | Cut 1.5" pieces of tubing | IP
|  |  | Wrap snake in loom | IP
|  | Get sensors ready |  | IP
|  |  | Solder wire & sensor to PCB | IP
|  |  | Connectors on | IP
|  |  | Address | IP
|  | Connector? |  | F |  | Red | 2019-03-28
|  | Extend cables? |  | OH | See if we actually need to do this before doing it (where will snake be positioned relative to mast)
|  | "Pot" sensors |  | IP
|  |  | Test/Experiment with potting | F |  |  | 2019-03-14
|  |  | Use frozen epoxy for potting | F |  |  | 2019-03-13
|  |  | "Pot" sensors that are already soldered | F |  |  | 2019-05-03
|  | Order Parts |  | F |  |  | 2019-05-07
|  | Test and address sensors that have been soldered |  | IP
Soil Sensor/Structure
|  | Assemble soil sensor structures (45 + 12NC = 57) |  | IP
|  |  | Cut 5" sections of 1" PVC (25 more will make 45 total, 37 will make 57 total) | IP
|  | "Pot" sensors |  | IP
|  |  | Pot sensors in cap | IP
|  |  | Pot cap into elbow | IP
|  |  | "Pot" sensors that are already soldered | F |  |  | 2019-05-03
|  | How high to mount and sensed area? |  | F |  | 6-9 inches | 2019-03-27
|  | Extend cables |  | F |  |  | 2019-05-08
Electronics
|  | Servers (6 needed, make 8 just to have extra) |  | IP
|  | Clients (40 needed, make 45 if have time to make extra) |  | IP
IRT Misc
|  | Inventory sheet |  | F |  |  | 2019-05-07
|  | Enclosures ready |  | IP
|  | Structure |  | IP
|  |  | Cut Plant Props | IP
|  |  | Cut metal poles | F
|  |  | Cut gray PVC to 5' and 2.5' lengths | NS
|  |  | Cut 40 1-1/4" gray PVC connector pieces (~6") | F
|  |  | Drill holes in rotating tee | IP
|  |  | Drill hole/attach bolt to tee | IP
North Carolina
|  | Create 1 full example setup |  | F |  |  | 2019-06-10
|  |  | Canopy sensor/arm | F |  |  | 2019-06-10
|  |  | Soil? | F |  |  | 2019-06-10
|  | Snakes (12) |  | F |  |  | 2019-06-10
|  | Canopy sensors (12) |  | F |  |  | 2019-06-10
|  | Soil sensors (12) |  | F |  |  | 2019-06-10
|  | Servers (3) (1 spare) |  | F |  |  | 2019-06-10
|  | Clients (14) (2 spare) |  | F |  |  | 2019-06-10
|  | Create a parts list |  | F |  |  | 2019-06-10
|  | Want the soil sensor? |  | F |  |  | 2019-06-10
|  | Assembly Protocol wit pics |  | IP
|  | Intallation/Setup Protocol |  | IP
Arduino/Board
|  | Get specifics about what Justin's doing |  | F |  |  | 2019-03-13
|  |  | Calculate storage capacity of server/client | F |  |  | 2019-03-13
|  | Adjust program? |  | F |  | Justin
|  | Redo components of board? |  | F |  | Justin
|  | Power |  | F
|  |  | Type/size/quantity of batteries | F |  | 12V! | 2019-03-14
|  |  | Solar panels - Which do we need? | F |  | Big ones from CIG | 2019-03-14
|  | Circuit between solar panel and board to stop charge from dissipating at night, and the battery from overcharging during the day |  | F |  | See if it works | 2019-05-01
FSP
| Dataloggers ready |  |  | F |  |  | 2019-06-01
|  | Ask Alondra what goes into this |  | F |  |  | 2019-06-01
| Soil water sensors ready/Install |  |  | IP
|  | Ask Alondra what goes into this |  | F |  |  | 2019-06-12
| Find Dennis's CS655 sensors |  |  | F | Just gave him others |  | 2019-04-15
CCSP
| Dataloggers ready |  |  | F |  |  | 2019-06-01
|  | Ask Alondra what goes into this |  | F |  |  | 2019-06-01
| Soil water sensors ready/Install |  |  | IP
|  | Ask Alondra what goes into this |  | F |  |  | 2019-03-14
| Put staples on gaskets to hold them on |  |  | F |  |  | 2019-03-07
Misc
| Assemble face shield |  |  | F |  |  | 2019-03-04
| Epoxy safety & usage info |  |  | F |  |  | 2019-03-04
| Make "to-do" sheet |  |  | F |  |  | 2019-03-05
| Windshield Wipers |  |  | F |  |  | 2019-03-11
| Help Alondra at CCSP - cable |  |  | F |  |  | 2019-03-12
| CCSP - check on battery power and radio lights on main logger |  |  | F |  |  | 2019-03-14